## WORKPLAN
KDSP II Level I Grant Workplan FY 2025/ 2026
KRA/DLI | Expected Output/Deliverable | Activity Description | Sub-Activities | Unit | No. of Units | Unit Cost (KES) | Total Cost (KES) | Start Date | End Date | Lead Dept
KRA 1: Sustainable Financing nad Expenditure Management
(DLI 2) Participating counties that have put in place core governance arrangements to manage public funds | SPMUs established & operational | Develop structures & job descriptions for SPMUs | i) Sensitization workshops for SPMU members | Workshops/ | 1 | 500000 | 500000 | Q1 | Q4 | Public Service & Administration
|  |  | ii) Training sessions on financial management | Training | 1 | 500000 | 500000
|  |  | iii) Procurement of office equipment & ICT tools | Equipment | 1 | 2605000 | 2605000
Increased county OSR collection by at least 5 % annually (DLI 3) | Enhanced county OSR collection | Review county OSR guidelines on revenue mapping and forecasting tools | i) Hire consultant for OSR gap and mapping analysis | Consultant/Technical Assistance | 1 | 2211308.46 | 2211308.46 | Q1 | Q4 | Finance & Economic Planning-Revenue Division
|  |  | ii) Training staff on forecasting models | Training | 1 | 400000 | 400000
|  |  | iii) Stakeholder validation workshop | Workshops | 1 | 500000 | 500000
Increased county OSR collection by at least 5 % annually (DLI 3) | Revenue base expanded | Develop and review revenue enhancement plans | i) Clean up of tax registers | Field visits and validation reports | 1 | 1700000 | 1700000 | Q2 | Q4 | Finance & Economic Planning-Revenue Division
|  |  | ii) Review and update of the existing revenue laws and regulations | Review meetings | 1 | 300000 | 300000
|  |  | iii) Dissemination workshops | Workshops | 1 | 300000 | 300000
Increased county OSR collection by at least 5 % annually (DLI 3) | Automated revenue collection | Develop technical specifications for upgraded integrated county revenue management system | i) Draft business process requirements | Consultant/Technical Assistance | 1 | 700000 | 700000 | Q2 | Q4 | ICT & Revenue
|  |  | ii) ICT design validation workshop | Workshops | 1 | 600000 | 600000
|  |  | iii) Pilot testing in sub-counties | Field visits/Reports | 1 | 500000 | 500000
Commitments are kept within resources availability, action plans are implemented on time, bills are paid on time, and the stock of pending bills is kept to a minimum (DLI 4) | Pending bills reduced | Develop & implement time-bound action plans | i) Verification of pending bills | Trainings/Verification Meetings | 1 | 2403846.1538 | 2403846.1538 | Q1 | Q4 | Finance & Economic Planning-County Treasury & Audit Section
|  |  | ii) Repayment schedule |  | 1 | 2403846.1538 | 2403846.1538
|  |  | iii) Monitoring compliance |  | 1 | 2403846.1538 | 2403846.1538
SUB TOTAL 1 | [6 empty] | 18027846.9215
KRA 2: Intergovernmental Coordination, Institutional Performance, and Human Resource Management
Consolidated HR data for decision-making, improved payroll integrity, and budget control on staffing (DLI 5) | Consolidated HR data | Review organizational structures & payroll | i) HR audit & gap analysis | Audit | 1 | 4000000 | 4000000 | Q1 | Q4 | Public Service Board
|  |  | ii) HRMIS training | Training | 1 | 2000000 | 2000000
|  |  | iii) Validation of staffing lists | Validation meetings | 1 | 1000000 | 1000000
Consolidated HR data for decision-making, improved payroll integrity, and budget control on staffing (DLI 5) | HRMIS modules | Compliance checks on grading & salary structures | i) Salary structure review | Consultant/Workshops | 1 | 2375000 | 2375000 | Q2 | Q4 | Public Service and Administration
ii) Compliance workshops
iii) Publication of HR manuals
Accountability for results through performance management (DLI 6 | Accountability via performance | Implement performance framework | i) Develop appraisal tools | Consultant | 1 | 1326923 | 1326923 | Q3 | Q4 | Public Service and Administration
|  |  | ii) Train department heads | Workshops | 1 | 2000000 | 2000000
|  |  | iii) Quarterly performance reviews | Workshops | 1 | 1000000 | 1000000
SUB TOTAL 2 | [6 empty] | 13701923
KRA 3:Oversight, Participation and Accountability
Improved county public investments which are aligned to citizen service delivery needs (DLI 7) | Improved county public investments | Roll out PIM framework & manuals | i) Printing & dissemination | Manuals/Workshops | 1 | 1000000 | 1000000 | Q1 | Q4 | Public Service and Administration
ii) Staff induction workshops
iii) Public awareness campaigns
Improved county public investments which are aligned to citizen service delivery needs (DLI 7) | Citizen feedback on investments | Develop open public investment database | i) Database design & hosting | ICT System/Training | 1 | 1770230 | 1770230 | Q2 | Q4 | Public Service and Administration
ii) Training staff
iii) Launch with stakeholders
Improved county public investments which are aligned to citizen service delivery needs (DLI 7) | Inclusive project management | Develop guidelines for project committees | i) Stakeholder forums | Meetings/Guidelines | 1 | 1000000 | 1000000 | Q1 | Q4 | Planning & Social Services
ii) Draft guidelines
iii) Printing & dissemination
Improved county public investments which are aligned to citizen service delivery needs (DLI 7) | Resilient infrastructure | Climate resilience assessments | i) Field assessments | Field visits/Reports | 1 | 1000000 | 1000000 | Q3 | Q4 | Environment & Natural Resources
ii) Expert reports
iii) Validation workshop
Improved county public investments which are aligned to citizen service delivery needs (DLI 7) | Transparent monitoring | Project stocktaking | i) Field visits | Field visits/Reports | 1 | 1000000 | 1000000 | Q3 | Q4 | Public Service and Administration-M&E Unit
ii) Data collection & reporting
iii) Dissemination of findings
SUB TOTAL 3 | [6 empty] | 5770230
TOTAL | [6 empty] | 37499999.9215
PREPARED BY: | BENEDICT KUTTO
PROGRAM COORDINATOR
CHECKED BY: | MEBAKARI MWATABU
CHIEF OFFICER INCHARGE OF DEVOLUTION

## CASHFLOW
KDSP II Level I Grant Cashflow FY 2025/ 2026
KRA/DLI | Activity | Sub-Activities | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Total (KES)
KRA 1 (DLI 2) | Establish SPMUs | Sensitization workshops | 0 | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
|  | Training sessions | - | - | 250000 | 250000 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
|  | Office equipment procurement | - | - | - | 1300000 | 1305000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2605000
KRA 1 (DLI 3) | OSR Forecasting | Consultant gap analysis | - | - | - | 1105769 | 1105539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2211308
|  | Staff training | - | - | - | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
|  | Validation workshop | - | - | - | - | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
KRA 1 (DLI 3) | Revenue Enhancement Plans | Tax register cleanup | - | - | - | 566667 | 566667 | 566666 | 0 | 0 | 0 | 0 | 0 | 0 | 1700000
|  | Review of laws | - | - | - | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
|  | Dissemination workshops | - | - | - | - | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
KRA 1 (DLI 3) | Integrated Revenue System | Draft business process | - | - | - | 350000 | 350000 | - | 0 | 0 | 0 | 0 | 0 | 0 | 700000
|  | ICT validation workshop | - | - | - | - | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
|  | Pilot testing | - | - | - | - | - | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 500000
KRA 1 (DLI 4) | Pending Bills Action Plan | Verification of bills |  |  |  | 0 | 0 | 0 | 801282 | 801282 | 801282 | 0 | 0 | 0 | 2403846
|  | Repayment schedule |  |  |  | 0 | 0 | 0 | 801282 | 801282 | 801282 | 0 | 0 | 0 | 2403846
|  | Monitoring compliance |  |  |  | 0 | 0 | 0 | 801282 | 801282 | 801282 | 0 | 0 | 0 | 2403846
KRA 2 (DLI 5) | HR Data Consolidation | HR audit | - | - | - | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 4000000
|  | HRMIS training | - | - | - | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
|  | Validation staffing lists | - | - | - | - | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
KRA 2 (DLI 5) | Salary Compliance Checks | Salary structure review | - | - | - | - | 1187500 | 1187500 | 0 | 0 | 0 | 0 | 0 | 0 | 2375000
KRA 2 (DLI 6) | Perf. Mgmt Framework | Appraisal tools | - | - | - | - | - | - | 663462 | 663461 | 0 | 0 | 0 | 0 | 1326923
|  | Train dept. heads | - | - | - | - | - | - | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 2000000
|  | Quarterly reviews | - | - | - | - | - | - | 500000 | 500000 | 0 | 0 | 0 | 0 | 1000000
KRA 3 (DLI 7) | PIM Rollout | Printing & dissemination |  |  | - | - | - | - | - | - | 0 | 500000 | 500000 | 0 | 1000000
| Citizen Database | Design & hosting | - | - | - | - | 884616 | 885615 | - | - | 0 | 0 | 0 | 0 | 1770231
| Project Guidelines | Stakeholder forums |  |  | - | - | - | - | 500000 | 500000 | 0 | 0 | 0 | 0 | 1000000
| Climate Resilience | Field assessments | - | - | - | - | - | - | - | - | 500000 | 500000 | 0 | 0 | 1000000
| Stocktaking | Field visits | - | - | - | - | - | - | - | - | 500000 | 500000 | 0 | 0 | 1000000
TOTAL |  |  | 8760615 | 8610615 | 3903846 | 3966667 | 6093283 | 3439781 | 2913462 | 2163461 | 1000000 | 1000000 | - | - | 37500000
PREPARED BY: | BENEDICT KUTTO
PROGRAM COORDINATOR
CHECKED BY: | MEBAKARI MWATABU
CHIEF OFFICER INCHARGE OF DEVOLUTION

## BUDGET
KDSP II Level I Grant Budget FY 2025/ 2026
No. | Activity | Responsible Party for Implementation | Start Date | End Date | Budget (KES)
1 | Sensitization workshops for SPMU members | Public Service & Administration | Q1 | Q4 | 500000
2 | Training sessions on financial management for SPMUs | Public Service & Administration | Q1 | Q4 | 500000
3 | Procurement of office equipment & ICT tools for SPMU | Public Service & Administration | Q1 | Q4 | 2605000
4 | Hire consultant for OSR gap and mapping analysis | Finance & Economic Planning – Revenue Division | Q1 | Q4 | 2211308
5 | Training staff on forecasting models | Finance & Economic Planning – Revenue Division | Q1 | Q4 | 400000
6 | Stakeholder validation workshop on OSR forecasting | Finance & Economic Planning – Revenue Division | Q1 | Q4 | 500000
7 | Clean-up of tax registers | Finance & Economic Planning – Revenue Division | Q2 | Q4 | 1700000
8 | Review and update of existing revenue laws & regulations | Finance & Economic Planning – Revenue Division | Q2 | Q4 | 300000
9 | Dissemination workshops on revenue laws | Finance & Economic Planning – Revenue Division | Q2 | Q4 | 300000
10 | Draft business process requirements for revenue management system | ICT & Revenue | Q2 | Q4 | 700000
11 | ICT design validation workshop | ICT & Revenue | Q2 | Q4 | 600000
12 | Pilot testing of revenue management system in sub-counties | ICT & Revenue | Q2 | Q4 | 500000
13 | Verification of pending bills | Finance & Economic Planning – County Treasury & Audit Section | Q1 | Q4 | 2403846
14 | Development of repayment schedule for pending bills | Finance & Economic Planning – County Treasury & Audit Section | Q1 | Q4 | 2403846
15 | Monitoring compliance to pending bills repayment | Finance & Economic Planning – County Treasury & Audit Section | Q1 | Q4 | 2403846
16 | HR audit & gap analysis | Public Service Board | Q1 | Q4 | 4000000
17 | HRMIS training | Public Service Board | Q1 | Q4 | 2000000
18 | Validation of staffing lists | Public Service Board | Q1 | Q4 | 1000000
19 | Salary structure review | Public Service & Administration | Q2 | Q4 | 2375000
20 | Develop appraisal tools | Public Service & Administration | Q3 | Q4 | 1326923
21 | Train department heads on performance framework | Public Service & Administration | Q3 | Q4 | 2000000
22 | Quarterly performance reviews | Public Service & Administration | Q3 | Q4 | 1000000
23 | Printing & dissemination of PIM framework/manuals | Public Service & Administration | Q1 | Q4 | 1000000
24 | Database design & hosting for public investment database | Public Service & Administration | Q2 | Q4 | 1770231
25 | Stakeholder forums for project management committees | Planning & Social Services | Q1 | Q4 | 1000000
26 | Field assessments on climate resilience | Environment & Natural Resources | Q3 | Q4 | 1000000
27 | Project stocktaking – field visits & reporting | Public Service & Administration – M&E Unit | Q3 | Q4 | 1000000
| TOTAL |  |  |  | 37500000
| PREPARED BY: | BENEDICT KUTTO
PROGRAM COORDINATOR
| CHECKED BY: | MEBAKARI MWATABU
CHIEF OFFICER INCHARGE OF DEVOLUTION

## Allocation Formula
DLI | 2024-25 | 2025-26
2 | 250000 | 250000
3 |  | 500000
4 |  | 500000
5 |  | 650000
6 |  | 300000
7 |  | 400000
TOTAL (USD) | 250000 | 2600000
| 37500000 | 390000000 | Assuming previous exchange rate of Kshs 150
357500000
DLI | % Share | Allocation
2 | 9.6154 | 3605769.2308
3 | 19.2308 | 7211538.4615
4 | 19.2308 | 7211538.4615
5 | 25 | 9375000
6 | 11.5385 | 4326923.0769
7 | 15.3846 | 5769230.7692
37500000