## BUDGET & GANT CHART
Table1: County Investment Budget FY 2025/2026
# | Project Activity | Timeframe |  | Budget
|  | Start date | End date | Kshs
1 | Tarmacking of Ndavaya-Deri-Mtsamviani road | 2025-10-01 | 2026-11-01 | 200000000
2 | Tarmacking of Shimba Hills-Kona Ya Masai road | 2025-10-01 | 2026-11-01 | 152500000
| Total |  |  | 352500000
Table 2: Gantt Chart – County Investment Budget FY 2025/2026
# | Activity | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
1 | Tarmacking of Ndavaya–Deri–Mtsamviani road |  |  |  | █ | █ | █ | █ | █ | █ | █ | █ | █
2 | Tarmacking of Shimba Hills–Kona ya Masai road |  |  |  | █ | █ | █ | █ | █ | █ | █ | █ | █
Legend: █ = Active Implementation
;